## Sheet1
User Story | Story Points (Fibonacci) | Owner | Progress
As a user, I want to right click a dot in the workspace and select "Delete", so that the connection gets deleted. | 8 | Chandan | Completed
As a user, I want to right click a bar in the workspace and select "Delete", so that all the connections get deleted. | 8 | Raghavan | Completed
As a user, I want to be able to scroll both vertically, horizonatally, so that I can navigate the whole window when I resize my window. | 3 | Rishika | Completed
As a user, I want to resize the application window. | 1 | Chandan | Completed
As a user, I want to right click a dot/bar in the workspace, so that I get a dialog menu with confirmation to delete. | 3 | Raghavan | Completed
As a user, I want to drag icons in the left panel onto the workspace so that I can create a new icon in the workspace. | 3 | Mayank | Completed | Days Remaining | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1
As a user, I want to double click on "#" in the workspace, enter a name in the dialog box, so that I can update the tab name with the same name. | 5 | Parikshith | Completed | Tasks Remaining | 71 | 68 | 62 | 50 | 42 | 30 | 20 | 8 | 0
As a user, I want to right click an icon in the workspace, so that I can delete the icon along with its connections. | 5 | Parikshith | Completed | Ideal | 71 | 62 | 53 | 44 | 35 | 26 | 17 | 8 | 0
As a developer, I want to compile with "#" icon so that I can check if it is compiling all the tabs connected. | 5 | Mayank | Completed
As a user, I want a menu named "Project" with two options, "Complie", "Translate", so that I can click on them. | 2 | Parikshith | Completed
As a user, I want a tool bar below the menu bar, above the workspace with the available icons, so that I can click on them. | 3 | Rishika | Completed
As a user, I want a new icon "#" in my left panel as well as in tool bar, so I can use them to create new icon in the workspace. | 2 | Rishika | Completed
As a user, I want to click on any icon in the tool bar then click anywhere in the workspace so that I can create a new icon in the workspace. | 2 | Rishika | Completed
As a user, when I create a new "#" in the workspace I want a new tab, so that I can click on the tab. | 5 | Mayank | Completed
As a user, I want to minimize the application on click of minimize button in the title bar. | 2 | Parikshith | Completed
As a user, I want to maximize the application on click of maximize button in the title bar. | 1 | Mayank | Completed
As a user, I want to click on close button in the title bar, so that I can close the application. | 1 | Rishika | Completed
As a user, I want to have only one open bracket per tab. | 2 | Raghavan | Completed
As a user, I want to have only one close bracket per tab. | 2 | Raghavan | Completed
As a user, I want to click on "Translate" option in Project menu to generate a code, so that I can verify my graph. | 5 | Chandan | Completed
As a user, I want to get an error message dialog box on click of compile button so that I can identify which connections are missing. | 3 | Rishika | Completed