## Sheet1
Sprints | Sprint 1 | [7 empty] | Sprint 2
Tasks/Days | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday
1. As a user, I want a frame with two panels seperated vertically.
a. Create a frame and add 2 panels. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Split panels Vertically. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. As a user, I want menu bar containing 2 labels- File to have menus like make, save, open a file and Project having compile and Translate.
c. Create a menu bar with 2 Jmenu- File and Project. | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Add sub menus to File - New, Open and Save. | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
c. Add sub menus to Project - Compile and Translate. | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. As a user, I should be able to have toolbar below the menu bar so that I can have figures displayed in it.
a. Create a tool bar using JToolBar. | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Place it below menubar. | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. As a user, I want a rectangle shape at the top of the left panel and toolbar with ')' symbol at its center and a dot right to the symbol.
a. Create a Button with Rectangle shape. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Add the text symbol '(' at the center of rectangle. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
c. Create a Component with dot. | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
d. Add the dot component near right side of rectangle. | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
f. Add the rectangle button at the left most corner of toolbar. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
f. Add the rectangle button at the top of the left panel. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. As a user, I want a rectangle after first rectangle in leftpanel and toolbar with '(' symbol at its center and a dot left to the symbol.
a. Create a Button with Rectangle shape. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Add the text symbol ')' at the center of rectangle. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
c. Add the dot component near left side of rectangle. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
d. Add the rectangle button below first rectangle of the left panel. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. As a user, I want a rectangle below second rectangle with '<' symbol at its center and 1 dot left and 2 dots right to the symbol.
a. Create a Button with Rectangle shape. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Add the text symbol '<' at the center of rectangle. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
c. Add 1 dot near left side and 2 dots near right side of rectangle. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
d. Add the rectangle button below second rectangle of the left panel. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
e. Add the rectangle button after first rectangle in toolbar. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7. As a user, I want a rectangle after third rectangle with '>' symbol at its center and 2 dots to left and 1 dot right to the symbol.
a. Create a Button with Rectangle shape. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Add the text symbol '>' at the center of rectangle. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
c. Add 1 dot near right side and 2 dots near left side of rectangle. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
d. Add the rectangle button below third rectangle of the left panel. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
e. Add the rectangle button after second rectangle in toolbar. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8. As a user, I want a rectangle after fourth rectangle with '@' symbol at its center and 2 dots left and 2 dots right to the symbol.
a. Create a Button with Rectangle shape. | 0 | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Add the text symbol '@' at the center of rectangle. | 0 | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
c. Add 2 dots near right side and 2 dots near left side of rectangle. | 0 | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
d. Add the rectangle button below fourth rectangle of the left panel. | 0 | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
e. Add the rectangle button after third rectangle in toolbar. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9. As a user, I want a rectangle below fifth rectangle with '¦¦' symbol at its center and 2 bars, one to left and other right to the symbol.
a. Create a Button with Rectangle shape. | 0 | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Add the text symbol '¦¦' at the center of rectangle. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
c. Add 2 bars, one near left side and another near right side of rectangle. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
d. Add the rectangle button below fifth rectangle of the left panel. | 0 | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
e. Add the rectangle button after fourth rectangle in toolbar. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10. As a user, I want a rectangle below sixth rectangle with '-' symbol at its center and 2 dots, one to left and another right to symbol.
a. Create a Button with Rectangle shape. | 0 | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Add the text symbol '-' at the center of rectangle. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
c. Add 2 dots, one near left side and another near right side of rectangle. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
d. Add the rectangle button below sixth rectangle of the left panel. | 0 | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
e. Add the rectangle button after fifth rectangle in toolbar. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11. As a user, I want a rectangle below seventh rectangle with '#' symbol at its center and 2 dots, one to left and another right to symbol.
a. Create a Button with Rectangle shape. | 0 | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Add the text symbol '#' at the center of rectangle. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
c. Add 2 dots, one near left side and another near right side of rectangle. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
d. Add the rectangle button below seventh rectangle of the left panel. | 0 | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
e. Add the rectangle button after seventh rectangle in toolbar. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12. As a user, I should be able to select any of the shape in toolbar by clicking on it.
a. Add action listener for all the shape objects of toolbar. | 0 | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Create a variable in singleton class to store all the data related to selected shape. | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13. As a user, I should be able to drag an instance of any shape in left panel to right panel.
a. Add action listener for all the shape objects of left panel. | 0 | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Store the screen co-ordinates of the shape when mouse pressed event of the shape object occurs. | 0 | 0 | 0 | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
c. Repaint the instance of object component at the current mouse co-ordinates. | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14. As a user, I should be able to click in the current tab so that the selected shape in toolbar is drawn at the clicked position.
a. Add a Mouse click Listener on all the tabs in right panel. | 0 | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Add selected shape in right panel at the clicked position. | 0 | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15. As a user, I should be able to drag any shape in the right panel.
a. Add mouse pressed listener to all shape objects. | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Store the screen co-ordinates of the when mouse pressed event of the shape object occurs. | 0 | 0 | 0 | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
c. Repaint the object component at the co-ordinates. | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16. As a user, I should be able to save information in any shape.
a. Modify the mouse clicked listener to accommodate mouse double click event to open input dialouge box. | 0 | 0 | 0 | 0 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Store the string value entered in the in the input dialouge box. | 0 | 0 | 0 | 0 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17. As a user, I should be able to get a new tab when double clicked on Shape # and save its name in the dialogue box.
a. Modify the mouse clicked listener to accommodate mouse double click event to open new tab and a dialogue box. | 0 | 0 | 0 | 0 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Store the string value entered in the input dialouge box. | 0 | 0 | 0 | 0 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18. As a user I should be able to draw a line from dots.
a. Add mouse clicked listener to Dot component. | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Store the co-ordinates of the Dot component when clicked. | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
c. Maintain a variable in singlton class to check if already clicked on Dot. | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
d. Draw a line using paint component when clicked on another dot or Bar. | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19. As a user I should be able to delete a line from dots or bars.
a. Add mouse clicked listener to Dot and bar component. | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Check for the co-ordinates of the Dot or bar component in connections when clicked with shift button. | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
c. Remove the cordinates from Connections | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
20. As a user I should be able to change the connection of a line from dots or bar.
a. Add mouse clicked listener to Dot or bar component. | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Store the co-ordinates of the Dot or bar component when clicked. | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
c. When clicked on dot or bar, change the connection cordinates for dots or bars. | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
d. Draw a line using paint component when clicked on another dot or Bar. | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21. As a user I should be having scroll bars attached to the frame.
a. Add scroll bar to window using JScrollBar. | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Add the bar for both horizontal and vertical orientation. | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22. As a user I should be able to draw lines from bars.
a. Add mouse clicked listener to Bar component. | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Store the co-ordinates of the Bar component when clicked. | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
c. Maintain a variable in singleton class to check if Dot or a Bar is already clicked. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
d. Draw a line using paint component when clicked on another dot or Bar. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23. As a system, I want any existing line to be dragged accordingly when any shape in right panel is dragged to a different position.
a. Store the new co-ordinates of the dragged shape and its dot and bar components. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0
b. Repaint the line using new co-ordinates. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0
24. As a system, when user clicks on Compile button, I should be able to check if the graph drawn on current tab is correct.
a. Add Mouse Click Listener on Compile button to create graph from the shapes drawn in current tab. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
b. Write a function to validate the graph. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0
c. Show a dialouge box represeting the output of compilation. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
25. As a system, when user clicks on translate button, dialogue box having code for generating structural graph equivalent appears.
a. Add Mouse Click Listener on Compile button to create list of the shapes drawn in all tabs and store their connections. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
b. Write a function to append the information in code which generated code compatible to graphviz compiler. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0
c. Show a dialouge box represeting the output of translate. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
26. As a system, when user, clicks save, I should be able to save co-ordinates of all the shapes and lines in right panel into a file.
a. Add mouse click listener on Save button. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
b. Add FileChooser event to select the directory and file name. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
c. Add co-ordinates of shapes stored in right panel. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
27. As a system, when user opens a new file, I should be able to redraw the shapes and lines in the right panel.
a. Add mouse click listener Save button. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
b. Add FileChooser event to select the directory and file name. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
c. Read co-ordinates of different shapes from the file and store it. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
d. Use the stored co-ordinates to repaint the shape objects. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
28. As a system, when user clicks on New, all tabs should be closed and a fresh work space should appear.
a. Add mouse click listener New button. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
b. Add FileChooser event to select the directory and file name. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
c. Add co-ordinates of shapes stored in right panel. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
d. Close all the tabs and open a new tab. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
e. Clean the code. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0