## Sheet1
Student | User Story | Tasks | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6
Ashwin | As a user, I need one menu bar with two drop down menus, so that they can display the File and Project options. | Add JMenuBar top of the frame | 1 | 0 | 0 | 0 | 0 | 0 | 1
|  | Populate dropdown in menu bar | 0 | 2 | 0 | 0 | 0 | 0 | 2
|  | Add OnClickListener to items in the menu bar | 0 | 0 | 2 | 0 | 0 | 0 | 2
|  | Unit testing | 0 | 0 | 0 | 1 | 0 | 0 | 1
|  | Total Hours | [6 empty] | 6
Ashutosh | As a user, I need a tool bar below the menu bar with a list of all the symbols, so that I can place each of the selected symbol on to the drawing area with a click. | Create a tool bar | 1 | 0 | 0 | 0 | 0 | 0 | 1
|  | add shapes to the tool bar | 3 | 0 | 0 | 0 | 0 | 0 | 3
|  | return the cordinates of the shapes clicked | 0 | 3 | 0 | 0 | 0 | 0 | 3
|  | update the information about the current shape selected | 0 | 0 | 1 | 1 | 0 | 0 | 2
|  | Unit testing | 0 | 0 | 0 | 1 | 0 | 0 | 1
|  | Total Hours | [6 empty] | 10
Chandan | As a user, I need a left panel with a list of all the shapes, so that I can drag & drop each of the shape on to the drawing area. | create a left panel and add shapes to it | 2 | 0 | 0 | 0 | 0 | 0 | 2
|  | implement drag and drop for the shapes | 2 | 1 | 0 | 0 | 0 | 0 | 3
|  | contsraint check for function block begin and end make sure they are draggable only one time per tab | 0 | 2 | 0 | 0 | 0 | 0 | 2
|  | Unit testing | 0 | 0 | 0 | 0 | 2 | 0 | 2
|  | Total Hours | [6 empty] | 9
Nachi | As a user, I need a ‘#’ symbol added to the list of shapes, so that I can place the shape on to the drawing area from both the list of shapes. | add hash icon to the tool bar | 0 | 1 | 0 | 0 | 0 | 0 | 1
|  | and hash icon to the drag and drop section | 0 | 1 | 0 | 0 | 0 | 0 | 1
|  | add input dialog action listener for the hash block | 0 | 0 | 2 | 1 | 0 | 0 | 3
|  | add action listener for the hash at the tool bar | 0 | 0 | 1 | 2 | 0 | 0 | 3
|  | Unit testing | 0 | 0 | 0 | 0 | 1 | 0 | 1
|  | Total Hours | [6 empty] | 9
Srini | As a user, when I double click the ‘#’ symbol on the drawing area, I should see a new tab which has a blank drawing area with a name that can be edited. | Knowledge acquistion on tabbed panes in java | 0 | 0 | 2 | 0 | 0 | 0 | 2
|  | on dropping hash icon create a new tab | 0 | 0 | 2 | 0 | 0 | 0 | 2
|  | connect to input dialog box for the user to name the newly created tab | 0 | 0 | 0 | 2.5 | 0 | 0 | 2.5
|  | add close option for the input dialog box | 0 | 0 | 1 | 1 | 0 | 0 | 2
|  | Unit testing | 0 | 0 | 1 | 1 | 0.5 | 0 | 2.5
|  | Total Hours | [6 empty] | 11
Srini | As a user, I should be able to ‘delete’ the nodes, connection between any of the nodes on right click, so that I can modify the diagram. | add listenter for the right click in java | 0 | 0 | 0 | 2 | 0 | 0 | 2
|  | identify the node on the drawing area to delete | 0 | 0 | 0 | 0 | 2 | 0 | 2
|  | identify the link clicked on the drawing area to delete | 0 | 0 | 0 | 0 | 0 | 1 | 1
|  | change the existing connections between nodes after deleteing the shape from the drawing list | 0 | 0 | 0 | 0 | 0 | 2.5 | 2.5
|  | change the existing connections between nodes after deleteing the shape from the drawing list | 0 | 0 | 0 | 0 | 0 | 2 | 2
|  | Total Hours | [6 empty] | 9.5
Srini | As a user, I should be able to change the connections between nodes, so that I can modify the diagram. | Knowledge Acquistion on java Graphics | 2 | 0 | 0 | 0 | 0 | 0 | 2
|  | on first click identity the shape selected | 0 | 2 | 0 | 0 | 0 | 0 | 2
|  | prompt the suer to select the second shape for the connection to be changed | 0 | 1 | 1 | 0 | 0 | 0 | 2
|  | reorder the links the playground | 0 | 0 | 1 | 0 | 0 | 0 | 1
|  | change the exting connection betwene the nodes appropriately | 0 | 0 | 0 | 1 | 0 | 0 | 1
|  | Unit testing | 0 | 0 | 0 | 1 | 0 | 0 | 1
|  | Total Hours | [6 empty] | 9
Srini | As a user, I should be able to use only one set of round brackets in the drawing area per tab. | control the behaviour of user selection in each tab | 0 | 0 | 0 | 1 | 0 | 0 | 1
|  | identify the shape selected by the user in the playground | 0 | 0 | 0 | 0 | 2 | 0 | 2
|  | prompt the user if function block begin or end is added to. tab more than once | 0 | 0 | 0 | 0 | 0 | 2 | 2
|  | delete option for the prompt | 0 | 0 | 0 | 0 | 0 | 1 | 1
|  | Unit testing | 0 | 0 | 0 | 0 | 0 | 1 | 1
|  | Total Hours | [6 empty] | 7
Srini | As a user, I should see a ‘Translate’, 'Compile' option in the Project options, 'save', 'load' in Project,File dropdown menu on the Menu bar. | add menu options save, load as drop down to the File options | 0 | 0 | 0 | 0 | 1 | 0 | 1
|  | add translate, compile as dropdown to the project section | 0 | 0 | 0 | 0 | 1 | 0 | 1
|  | test the existing existing save and load functionality | 0 | 1 | 1 | 0 | 3 | 0 | 5
|  | Unit testing | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5
|  | Total Hours | [6 empty] | 8.5
Srini | As a user, when I click on the ‘Translate’ option, I should see a structured set of instructions that represent the diagram in the drawing area. | Knowledge Acquistion on java algorithms | 2 | 0 | 0 | 0 | 0 | 0 | 2
|  | implement depth first search to identify all the connections between nodes | 0 | 2 | 2 | 0 | 0 | 0 | 4
|  | build a sparse matrix as a representation of the shapes | 0 | 0 | 0 | 1.5 | 1 | 0 | 2.5
|  | generate code snippets with the help of generated sparse matrix | 0 | 0 | 1 | 2 | 0 | 0 | 3
|  | populate the generated code on a input dialog for the user to copy paste to graph viz | 0 | 0 | 0 | 1 | 0 | 0 | 1
|  | Unit testing | 0 | 0 | 0 | 1 | 1 | 1 | 3
|  | Total Hours | [6 empty] | 15.5
Srini | As a user, when I click on ‘Compile’ option, in case of an error, I should get an error message that will indicate the tab on which the error exists. | Knowledge Acquistion on java algorithms | 2 | 0 | 0 | 0 | 0 | 0 | 2
|  | compile the existing diagrams with required constraints in place | 0 | 2 | 0 | 0 | 0 | 0 | 2
|  | do depth first search to identifyt he connected nodes | 0 | 1 | 1 | 0 | 0 | 0 | 2
|  | add error statements for each of the tabs individually | 0 | 0 | 1 | 0 | 0 | 0 | 1
|  | display the error log to the user on pop up | 0 | 0 | 0 | 1 | 0 | 0 | 1
|  | Unit testing | 0 | 0 | 0 | 1 | 0 | 0 | 1
|  | Total Hours | [6 empty] | 8
Srini | As a user, I need to see scroll bars on the drawing area, so that when I resize the window I can navigate through the diagram. | resize the frame | 1 | 0 | 0 | 0 | 0 | 0 | 1
|  | minimize and close the frame | 0 | 1 | 0 | 0 | 0 | 0 | 1
|  | add horizontal and vertical bars on resize | 0 | 1 | 1 | 0 | 0 | 0 | 2
|  | fit the drawinfg area to the frame | 0 | 0 | 1 | 0 | 0 | 0 | 1
|  | Unit testing | 0 | 0 | 1 | 0 | 0 | 0 | 1
|  | Total Hours | [6 empty] | 5
|  | Total Sprint Hours | [6 empty] | 107.5